## Project_Charter
DELIVERABLE MODULE 3 - PROJECT CHARTER
Project Title: Lean Process Improvement NovaPoint
|  |  |  | Black Belt | Project Champion | Executive Sponsor |  | MBB/Mentor
|  |  |  | C. Pope | Todd Peterson | Andy Myers |  | Michael Bell
Problem Statement |  |  |  |  | Business Case
Customers are dissatisfied with product being either too thick/thin due to variations with manufacturing leading to waste of resources/clients/raw materials and money |  |  |  |  | Increase the value by reducing variations in the quality of machines,
manpower, factory setting, to overall prevent the thin/thick issue and
reduce waste.
Project Goals |  |  |  |  | Project Scope
Increase first pass quality (FPQ) to 99% and reduce holds by 10% |  |  |  |  | Tempurature of factory
Consistancy of machinery/operators
Timing and training
High Level Project Timeline |  |  | Constraints & Dependencies |  | Project Risks |  | Additional Information
Phase | Start | Finish | Manning/personnel |  | If left uncorrected the variation will continue to cause waste in numerous forms leading to loss of resources, revenue, clientel, and raw materials |  | Production varries upon GPC card holder availability and budget allowance within each individual supplier chain.
Identify Value | present | 4 month | Machines
Map the Value Stream | 1 month | 5 month | Climate/tempurature
Create Flow | 1 month | 5 month
Establish Pull | 2 month | 6 month
Seek Perfection | 3 month | 6 month
Approval/Steering Committee |  |  |  | Stakeholders & Advisors |  | Project Team & SME's
Name |  | Organization |  | Name | Organization | Name |  | Organization
J. Bird |  | 355 WG/CEO |  | J. Bird | 355 WG/CEO | G. Stewart |  | 354th AMXS
C. Drummond |  | 355th CMS/setion chief |  | Y. Man | 355 GP/COO | S. Alt |  | 355th CMS
S. Alt |  | 355th CMS/GPC cardholder |  | C. Drummond | 355th CMS/Section Chief | F. Bouton |  | 355th CMS
|  |  |  | J. Embry | Top Supplier

## High Level Process Map
DELIVERABLE MODULE 4 - HIGH-LEVEL PROCESS MAP
Transfer icing to Kettle 2
• Place icing in Kettle 1
Complete a viscosity check
Transfer product to final assembly
Perform final quality check
Complete a shortening quality check
Package product

## SIPOC
DELIVERABLE MODULE 4 - SIPOC
Introduction and Instructions for SIPOC
SIPOC is an acronym that stands for supplier, input, process, output and customer
A SIPOC is a process mapping variant that for each process step identifies the inputs, the suppliers (internal or external) for those inputs, the outputs and the customers (internal or external) for that output
Using the template below, begin by filling in the "Process" column with the process steps identified in the high-level process map
Then, for each process step identify the inputs, the suppliers (internal or external) for the inputs, the outputs and the customers (internal or external) for the outputs
S.I.P.O.C. Template
| Suppliers | Inputs |  | Process | Outputs | Customers
| operators | icing
whip ice cream
operators
| operators | current whip
pass/fail
quality assurance
operators
whip from K1 that passed
ice cream
operators
ice cream whip
| operators |  |  |  | pass/fail | operators/QA
operators
|  | ice cream |  |  |  | operator
completed ice cream product
operators
|  | completed ice cream product |  |  | ice cream pass or fail
operator
operators
ice cream approved for delivery/packaging
final version of product
customer recieves
Place icing in kettel 1
Complete a shortening quality check
Transfer icing to Kettle 2
Complete a viscosity check
Transfer product to final assembly
Perform final quality check
Package product

## VSM
DELIVERABLE MODULE 4 - VSM
Value Stream Map
Supplier | [9 empty] | Customer
Information | [9 empty] | Information
|  |  | Shortening Quality Check |  |  | Icing Transfers to Kettle 2
| Icing in Kettle 1 | [6 empty] | Check Viscosity |  | Transfer to Final Assembly |  | Final Quality Check |  | Package Product
15 |  | 3 |  |  | 5 |  | 3 |  | 10 |  | 3 |  | 10
0.5
2
[12 empty] | 39 |  |  | 39
C/T
C/O
FPY
Holds
Process Step
1
39
3
39
1
39
1.5
39
6
39
C/T 1.0
C/O 0.0
FPY 85%
Holds 20%
C/T 6.0
C/O 0.5
FPY 98%
Holds0%
C/T 3.0
C/O 0.5
FPY 98%
Holds 0%
C/T 1.0
C/O 0.0
FPY 76%
Holds 25%
C/T 1.5
C/O 0.5
FPY 98%
Holds 0%
C/T 0.5
C/O 0.0
FPY 95%
Holds 5%
C/T 2.0
C/O 0.25
FPY 96%
Holds 0%
TOTAL
39
P/T
%C&A

## Cause_Effect_Diagram
DELIVERABLE MODULE 5- CAUSE AND EFFECT DIAGRAM
Instructions:
STEP 1 : Define the problem. What is the product, process or service that has failed.
| Wait times | keeping up with limits |  | product temp
STEP 2 : Starting with 'Materials' or any other label, ask: is there anything about materials that
| kettle time | understanding process |  |  |  | might contribute to the problem. Record it next to one of the arrows under Materials.
| temp |  |  |  |  | STEP 3 : Repeat asking "is there anything about materials that might contribute to the problem"
[5 empty] | Form/Viscosity of product (ice cream) inconsistant | Record each result next to an arrow.
STEP 4 : Repeat Step 2 & 3 for each successive category.
Tempurature and humidity/weather |  |  | Consistancy of mixing | Adequate functioning
STEP 5 : Identify the candidates that are the most likely Root Cause
|  |  | Waiting | Consistant product output
STEP 6 : If further "screening" is necessary, assess the likely Root Causes using the "Impact"
and "Implement" matrix, selecting items marked 1, then 2 . . . 4 as priorities.
Measurement
People (Man)
Materials
Environment (Mother Nature)
Methods
Machines

## Pareto
DELIVERABLE MODULE 5 - PARETO CHART
Categories | # of Occurrences
Water in pipe | 55
Liquid Sucrose | 25
Provider supplying out of spec material | 48
Clean out water not purged | 32
quality of shortening | 41
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## 5-Why's
DELIVERABLE MODULE 5 - 5 WHY'S
5-WHY ANALYSIS SHEET
Note: Continue on separate page if 5-Whys are not enough to determine root cause.
WHY ? #1:
Why is there water consistantly in the pipes?
Because the pipes are clogged.
WHY ? #5
WHy are we using poor material from this supplier?
The products/supplies were not inspected upon reciept.
WHY ? #2:
Why are the pipes always clogged?
Because the product used is still remaining post cleanup.
WHY ? #4
Why are there poor materials being used?
Because they were provided by suplier.
WHY ? #3
WHy is the cleanup not actually cleaning the pipes?
Because the product used is insufficient/effective in material standards.
TEMPORARY Date: 20211010
COUNTERMEASURES
Reach out to supplier to ensure proper specifcations are met to meet requirements for cleanup. Do a proper inspection of product upon arrival.
FINAL COUNTERMEASURE Name: C. Pope
- PERMANENT CORRECTIVE ACTION Date: 20211112
Inspection of materials upon reciept as well
as a post cleanup inspection
VERIFICATION:
No Recurrence in Three Months? TBD Date:
Single-Point Lesson? ____n/a_____ Date ________
DO THE 5 WHY'S MAKE SENSE WHEN READ BACKWARD?

## Waste Walk
DELIVERABLE MODULE 6 - WASTE WALK
8 Wastes/Waste Walks
Defects - Re-adjusting process parameters, reworking finished products, off spec materials |  |  | Defects
Overproduction - Making anything sooner, faster or in excess of customer requirements |  |  | Overproduction
Waiting - Waiting for raw materials, maintenance personnel, processes to finish, and instructions |  |  | Waiting
Non Utilized Talent - Workers not involved in improvement areas; input or feedback ignored. Changes without consulting workers and employees not challenged |  |  | Non Utilized Talent
Transportation - Putting products in work-in-progress areas and moving materials due to poor layout |  |  | Transportation
Inventory (Excess) - Work-in-progress, rework waiting for testing, excessive raw and finished products |  |  | Inventory
Motion (Excess) - Moving tools and people to defferent areas, excessing manual material movement |  |  | Motion
Excessive Processing - Excessive Quality checks, Performing operations not required |  |  | Excessive Processing
Waste Type | Describe the waste you saw
Defects | the consistancy of the ice cream being manufactured is out of spec/viscosity
Overproduction | because of the defective viscosity of ice cream additional product is being created
Waiting | kettle wait times
Inventory | inadequate because of the tolerance levels not being maintained
Non Utilized Talent | workers sit idle during mix when they could be doing something else in the mean time
Motion | inventory not being properly maintained
Excessive Processing | cleanups having to be reaccomplished regularly

## Root Cause Analysis
Deliverable Module 6 Root Cause Analysis
Root Cause Analysis (Please state your conclusions)
The cause of the pipes clogging is that the supplier/material inventors product is not always within allowable limits. This is do to an inconsisteient inventory from supplier. Likely course of action would be to get with supplier and have them fix their product to be within consistant and allowable limites/tolerances. Or to find a new supplier whose product is already within limits and is consistant.

## Kanban
DELIVERABLE MODULE 7 - KANBAN
KANBAN CARD
Part Description/Picture if Applicable | Part Number | Profile
Raw milk | DFCPJ0835 | consistent temp of 235 degrees (F) +/- 2 degrees with relative consistnacy/viscosity of 2Nwt
QTY. | Lead Time | Due Date
5 gallons | 15 minutes | current/day of
Supplier | Location | Card #
milk.inc | Kettle 855 | 1 OF 2
KANBAN CARD
Part Description/Picture if Applicable | Part Number | Profile
the thickening agent/product | DFCPJ0955 | relative thickness/consistancy/viscosity of 200 Nwts @ 235 degrees (F) with relative gravity comp.
QTY. | Lead Time | Due Date
55 Gallons | 30 minutes | day of/current
Supplier | Location | Card #
thickums LLC. | Kettle 856 | 2 OF 2

## Audit_Checklist
DELIVERABLE MODULE 7 - AUDIT
Audit Checklist
Target Area: | Statement of Audit Objective: | Auditor: | Audit Date:
Audit Technique | Auditable Item, Observation, Procedure etc. | Individual Auditor Rating (Circle Rating)
Observation | Have all associates been trained? | YES | NO
Observation | Is training documentation available? | YES | NO
Observation | Is training documentation current? | YES | NO
Observation | Are associates wearing proper safety gear? | YES | NO
Observation | Are SOP's available? | YES | NO
Observation | Are SOP's current? | YES | NO
Observation | Is quality being measured | YES | NO
Observation | Is sampling being conducted in random fashion | YES | NO
Observation | Is sampling meeting it's sample size target? | YES | NO
Observation | Are control charts in control | YES | NO
Observation | Are control charts current? | YES | NO
Observation | Is the process capability index >1.0? | YES | NO
Number of Out of Compliance Observations |  |  | 0
Total Observations |  |  | 50
Audit Yield |  |  | 100%
Corrective Actions Required |  |  | none
Auditor Comments
After overhall of supplier/manufacturers the pipeing system is being cleaned at acceptable rate. Product viscostiy is measuring at consistant levels. Management is ensuring proper training/SOPs/safety protocals are being followed and consistant follow up with front line supervisors and dock workers. Overall audit shows significant improvement and minimal wastes are bieng accrued and overall effeciency of the process is streamlined. A quarterly review takes place were the focus remains on perfection of the process.